## Studio Schedule
|  | STUDIO SCHEDULE 3.0 |  |  | Live Job | [6 empty] | Studio & Interactive | [6 empty] | M | Milestone | [5 empty] | D | Project Delivery | [5 empty] | Ph | Public Holiday | [5 empty] | O | Offsite | [5 empty] | AL | Annual Leave | [5 empty] | Sp | Special Leave | [5 empty] | Live Job | [6 empty] | Studio & Interactive | [6 empty] | M | Milestone | [5 empty] | D | Project Delivery | [5 empty] | Ph | Public Holiday | [5 empty] | O | Offsite | [5 empty] | AL | Annual Leave | [5 empty] | Sp | Special Leave | [5 empty] | Live Job | [6 empty] | Studio & Interactive | [6 empty] | M | Milestone | [5 empty] | D | Project Delivery | [5 empty] | Ph | Public Holiday | [5 empty] | O | Offsite | [5 empty] | AL | Annual Leave | [5 empty] | Sp | Special Leave | [5 empty] | Live Job | [6 empty] | Studio & Interactive | [6 empty] | M | Milestone | [5 empty] | D | Project Delivery | [5 empty] | Ph | Public Holiday | [5 empty] | O | Offsite | [5 empty] | AL | Annual Leave | [5 empty] | Sp | Special Leave
[5 empty] | Pitch | [6 empty] | Studio | [6 empty] | H | Hold | [5 empty] | S | Shoot | [5 empty] | / | Half Day | [5 empty] | L | Leave | [5 empty] | Cl | Carers Leave | [5 empty] | U | Unavailable | [5 empty] | Pitch | [6 empty] | Studio | [6 empty] | H | Hold | [5 empty] | S | Shoot | [5 empty] | / | Half Day | [5 empty] | L | Leave | [5 empty] | Cl | Carers Leave | [5 empty] | U | Unavailable | [5 empty] | Pitch | [6 empty] | Studio | [6 empty] | H | Hold | [5 empty] | S | Shoot | [5 empty] | / | Half Day | [5 empty] | L | Leave | [5 empty] | Cl | Carers Leave | [5 empty] | U | Unavailable | [5 empty] | Pitch | [6 empty] | Studio | [6 empty] | H | Hold | [5 empty] | S | Shoot | [5 empty] | / | Half Day | [5 empty] | L | Leave | [5 empty] | Cl | Carers Leave | [5 empty] | U | Unavailable
[5 empty] | Active Lead | [6 empty] | Interactive | [6 empty] | C | Confirmed | [5 empty] | Cv | Client Visit | [5 empty] | A | Available | [5 empty] | Os | Overseas | [5 empty] | S | Sick Leave | [5 empty] | Ab | Absent | [5 empty] | Active Lead | [6 empty] | Interactive | [6 empty] | C | Confirmed | [5 empty] | Cv | Client Visit | [5 empty] | A | Available | [5 empty] | Os | Overseas | [5 empty] | S | Sick Leave | [5 empty] | Ab | Absent | [5 empty] | Active Lead | [6 empty] | Interactive | [6 empty] | C | Confirmed | [5 empty] | Cv | Client Visit | [5 empty] | A | Available | [5 empty] | Os | Overseas | [5 empty] | S | Sick Leave | [5 empty] | Ab | Absent | [5 empty] | Active Lead | [6 empty] | Interactive | [6 empty] | C | Confirmed | [5 empty] | Cv | Client Visit | [5 empty] | A | Available | [5 empty] | Os | Overseas | [5 empty] | S | Sick Leave | [5 empty] | Ab | Absent
|  | Please see http://wiki if you haven't used the studio schedule before. |  |  | X | AUDA8421 (SP) | INTE2012 |  |  |  | Internal 2012 | Audi Vivid Projection | [5 empty] | X | X | INTE3013 (OB) | SPIN8000 |  |  |  | Experian | Marketing & PR | [5 empty] | X | X | DNSW8391 (NG) | COAT7924 |  |  |  | Coates | Dr. Who Vivid projection | [5 empty] | X | X | YVON8490 (RL) | SPIN1234 |  |  |  | Test Job | SanYo Water Projection | [5 empty] | X | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X
[5 empty] | X | BAUM8339 (SP) | SPINXXXX |  |  |  | DNA2 | Q Media | [5 empty] | X | X | INTE7361A | SPIN8045 |  |  |  | Barclays | Lead Gen | [5 empty] | X | X | SPIN8341 (JH) | WEST7995 |  |  |  | Westpac | Nissan Innovation Wall Shanghai | [5 empty] | X | X | SPIN8487 (RL) | SPIN8073 |  |  |  | Accura Brand Video | Simpson's Live Projection | [5 empty] | X | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X
[5 empty] | X | DNSW8268 (AH) | SPIN8060 |  |  |  | Motorola Scorpion | Vivid MCA Projection | [5 empty] | X | X | SOHO8229 (NG) | SPIN7712 |  |  |  | Dreamforce | Vivid Opera House Projection | [5 empty] | X | X | SPIN8264 (CB) | GPJB7999 |  |  |  | Shanghai Tower | ESI 221 San Francisco | [5 empty] | X | X |  | SPIN8138 |  |  |  | Samsung | [6 empty] | X | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X
[5 empty] | X | GPJH8189 (PM) | SPIN7962 |  |  |  | Motorola Tunnel HD | Digital Lead Capture Form | [5 empty] | X | X | SPINXXXX | PEDD6871 |  |  |  | Greensborough Aquatic | DNA2 | [5 empty] | X | X | SPIN8139 (CB) | WING8020B |  |  |  | AWM Remember Me | ESI 330 Hudson | [5 empty] | X | X |  | INNO8009 |  |  |  | Hyundai Comic Book | [6 empty] | X | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X
|  | http://wiki/index.php/Studio_Schedule |  |  | X | INTE2012 | SPINXXXX |  |  |  | GPJ Singapore | Internal 2012 | [5 empty] | X | X | SPIN8250 (PM) | SAIR7905 |  |  |  | Sydney Airport | Spinifex Connect | [5 empty] | X | X | INTE2013 (SP) | PROG8067 |  |  |  | Herbal Essence | Pitch for Meble | [5 empty] | X | X |  | SPIN8151 |  |  |  | Infiniti LE Concept Reformat | [6 empty] | X | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X | [13 empty] | X
start |  |  |  |  | MAY | MAY | MAY | MAY | MAY | MAY | MAY | MAY | MAY | MAY | MAY | MAY | MAY | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | JULY | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY
jobID |  | Jobs |  |  | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
10199 | SL | X | AUDA8421 (SP) | Audi Vivid Projection | INTE2012 MAY 20: C; SPINXXXX MAY 21: C; SPINXXXX MAY 22: C; SPINXXXX MAY 23: C; SPINXXXX MAY 24: D; Spinifex Connect JUNE 10: Ph
10186 | SL | X | BAUM8339 (SP) | Q Media | bar: Spinifex Connect JUNE 10
10156 | EP | X | DNSW8268 (AH) | Vivid MCA Projection | INTE2012 MAY 20: C; SPINXXXX MAY 21: C; SPINXXXX MAY 22: C; SPINXXXX MAY 23: C; SPINXXXX MAY 24: D; Spinifex Connect JUNE 10: Ph
10136 | IL | X | GPJH8189 (PM) | Digital Lead Capture Form | bar: Spinifex Connect JUNE 10
10000 | EL | X | INTE2012 | Internal 2012 | bar: Spinifex Connect JUNE 10
10179 | EL | X | INTE3013 (OB) | Marketing & PR | bar: Spinifex Connect JUNE 10
10110 | IL | X | INTE7361A | Lead Gen | bar: Spinifex Connect JUNE 10
10190 | SL | X | SOHO8229 (NG) | Vivid Opera House Projection | INTE2012 MAY 20: C; SPINXXXX MAY 21: C; SPINXXXX MAY 22: C; SPINXXXX MAY 23: C; SPINXXXX MAY 24: D; Spinifex Connect JUNE 10: Ph
10075 | IL | X | SPINXXXX | DNA2 | bar: Spinifex Connect JUNE 10
10182 | IL | X | SPIN8250 (PM) | Spinifex Connect | bar: Spinifex Connect JUNE 10
10198 | SL | X | DNSW8391 (NG) | Dr. Who Vivid projection | bar: INTE2012 MAY 20 to SPINXXXX MAY 24; Internal 2012 MAY 27 to Internal 2012 MAY 31; Spinifex Connect JUNE 10
10192 | EL | X | SPIN8341 (JH) | Nissan Innovation Wall Shanghai | bar: Spinifex Connect JUNE 10
10194 | SL | X | SPIN8264 (CB) | ESI 221 San Francisco | bar: Spinifex Connect JUNE 10
10170 | SL | X | SPIN8139 (CB) | ESI 330 Hudson | bar: Spinifex Connect JUNE 10
10202 | EP | X | INTE2013 (SP) | Pitch for Meble | bar: Spinifex Connect JUNE 10
10203 | SP | X | YVON8490 (RL) | SanYo Water Projection | bar: Spinifex Connect JUNE 10
10204 | SP | X | SPIN8487 (RL) | Simpson's Live Projection | bar: Spinifex Connect JUNE 10
desID |  | Design
170 | P4 | Jason French | bar: INTE2012 MAY 20 to SPINXXXX MAY 24; Spinifex Connect JUNE 10
100 | P3 | Jonny Old |  |  | INTE2012 MAY 20: H; SPINXXXX MAY 21: C; SPINXXXX MAY 22: C; Spinifex Connect JUNE 10: Ph
251 | P2 | Tim Canipel |  |  | INTE2012 MAY 20: H; SPINXXXX MAY 21: C; SPINXXXX MAY 22: C; SPINXXXX MAY 23: H; Spinifex Connect JUNE 10: Ph
172 | F3 | Jamie Tufrey | bar: X MAY 19 to SPINXXXX MAY 24; Internal 2012 MAY 27 to Internal 2012 MAY 31; Spinifex Connect JUNE 10
171 | F3 | Cathy Vicareti | bar: INTE2012 MAY 20 to SPINXXXX MAY 24; Spinifex Connect JUNE 10
3dID |  | 3D
105 | P3 | Pepin Portingale | bar: INTE2012 MAY 20 to SPINXXXX MAY 22; Spinifex Connect JUNE 10
176 | P3 | Nick Hunter | bar: INTE2012 MAY 20 to SPINXXXX MAY 22; Spinifex Connect JUNE 10
177 | P3 | Roy Christian | bar: INTE2012 MAY 20 to SPINXXXX MAY 24; Spinifex Connect JUNE 10
255 | F3 | Steve Casey | bar: Spinifex Connect JUNE 10
252 | F2 | Nathan Rule | bar: Spinifex Connect JUNE 10
257 | F2 | Ray Kristianto | bar: INTE2012 MAY 20 to SPINXXXX MAY 22; Spinifex Connect JUNE 10
2dID |  | 2D
183 | P4 | Matt Lock | bar: INTE2012 MAY 20 to SPINXXXX MAY 23; Spinifex Connect JUNE 10
184 | P4 | Daniel Harkness | bar: INTE2012 MAY 20 to SPINXXXX MAY 23; Spinifex Connect JUNE 10
186 | P4 | Will Skinner |  |  | INTE2012 MAY 20: C; SPINXXXX MAY 21: C; SPINXXXX MAY 22: C; SPINXXXX MAY 23: C; SPINXXXX MAY 24: C; Spinifex Connect JUNE 10: Ph; X JULY 25: L; X JULY 26: L; X JULY 29: L
187 | P4 | Achim John | bar: Spinifex Connect JUNE 10
188 | P1 | Joe Webber | bar: Spinifex Connect JUNE 10
253 | F3 | Richie Ellis | bar: INTE2012 MAY 20 to SPINXXXX MAY 23; Spinifex Connect JUNE 10
254 | F3 | Mike Simmons | bar: INTE2012 MAY 20 to SPINXXXX MAY 23; Spinifex Connect JUNE 10
256 | F2 | Chris Zwar | bar: INTE2012 MAY 20 to SPINXXXX MAY 22; Spinifex Connect JUNE 10
laID |  | Los Angeles
229 | P3 | Gilad Arazi | bar: Spinifex Connect JUNE 10
206 | P3 | Laurent Y. | bar: Spinifex Connect JUNE 10
232 | F2 | Fil Ruting | bar: Spinifex Connect JUNE 10
editID |  | Edit
226 | F2 | Freelance Editor | bar: Spinifex Connect JUNE 10
techID |  | Technical
202 | P3 | Alan Puah | bar: Spinifex Connect JUNE 10
203 | P3 | Lang Walker | bar: Internal 2012 MAY 29 to Internal 2012 MAY 31; SPIN8250 (PM) JUNE 3 to SAIR7905 JUNE 7; Spinifex Connect JUNE 10
intDevID |  | Interactive
204 | P4 | Rene Christen | bar: Spinifex Connect JUNE 10; Pitch for Meble JUNE 27 to Pitch for Meble JUNE 28; X JULY 1 to SPIN8151 JULY 5
205 | P4 | Jonothan Kafkaris | bar: Spinifex Connect JUNE 10
207 | P3 | Robert Shearing | bar: INTE2012 MAY 20 to SPINXXXX MAY 24; Internal 2012 MAY 27 to Internal 2012 MAY 31; SPIN8250 (PM) JUNE 3 to SAIR7905 JUNE 7; Spinifex Connect JUNE 10 to Spinifex Connect JUNE 14
242 | F3 | Dave Towey | bar: Spinifex Connect JUNE 10
234 | F2 | Clint Francis | bar: Spinifex Connect JUNE 10
235 | F2 | Tom Byrne | bar: Spinifex Connect JUNE 10
softDevID |  | Software Development
212 | P3 | Guillaume Bodi | bar: Spinifex Connect JUNE 10
213 | P3 | Gabor Zins | bar: Spinifex Connect JUNE 10
proID |  | Producers
146 | P3 | Meble Tin | bar: Spinifex Connect JUNE 10
147 | P3 | Cyril De Baeque | bar: Spinifex Connect JUNE 10
148 | P3 | Anthony Hickson | bar: Spinifex Connect JUNE 10
150 | P3 | Jake Soper | bar: Spinifex Connect JUNE 10
151 | P3 | Paul Maher | bar: Spinifex Connect JUNE 10
152 | P3 | Jo Hedley | bar: Spinifex Connect JUNE 10
258 | P3 | Nik Goldsworthy | bar: Internal 2012 MAY 31; Spinifex Connect JUNE 10
217 | P2 | Olivia Beal | bar: Spinifex Connect JUNE 10
218 | P1 | Sueann Paterson | bar: Spinifex Connect JUNE 10
headID |  | Heads of Creative
142 | P4 | Richard Lindsay | bar: Spinifex Connect JUNE 10
143 | P4 | Hai Tran | bar: Spinifex Connect JUNE 10
144 | P4 | Julian Shuchard | bar: Spinifex Connect JUNE 10
222 | P4 | Dan Burke | bar: Spinifex Connect JUNE 10
stuffID |  | Non Human
224 | N | Canon 5D
endID
Note on HN276: 3dsMax Generalist Shiney things specialist Fire and smoke simulation
Note on HN435: 3dsMax Generalist Character modelling and animation
Note on HN673: Maya Generalist Car and phone fixing Car shading and lighting Cloth simulation
Note on AG364: Notes for the week:

## variables
DATA STORAGE SHEET - DO NOT MODIFY
Start Date | lastJobID | lastResourceID | lastColourID | colourID
2013-05-19 | 10204 | 260 | 43 | 1 | X
2013-05-20 |  |  |  | 2 | X
2013-05-21 |  |  |  | 3 | X
2013-05-22 |  |  |  | 4 | X
2013-05-23 |  |  |  | 5 | X
2013-05-24 |  |  |  | 6 | X
2013-05-25 |  |  |  | 7 | X
2013-05-26 |  |  |  | 8 | X
2013-05-27 |  |  |  | 9 | X
2013-05-28 |  |  |  | 10 | X
2013-05-29 |  |  |  | 11 | X
2013-05-30 |  |  |  | 12 | X
2013-05-31 |  |  |  | 13 | X
2013-06-01 |  |  |  | 14 | X
2013-06-02 |  |  |  | 15 | X
2013-06-03 |  |  |  | 16 | X
2013-06-04 |  |  |  | 17 | X
2013-06-05 |  |  |  | 18 | X
2013-06-06 |  |  |  | 19 | X
2013-06-07 |  |  |  | 20 | X
2013-06-08 |  |  |  | 21 | X
2013-06-09 |  |  |  | 22 | X
2013-06-10 |  |  |  | 23 | X
2013-06-11 |  |  |  | 24 | X
2013-06-12 |  |  |  | 25 | X
2013-06-13 |  |  |  | 26 | X
2013-06-14 |  |  |  | 27 | X
2013-06-15 |  |  |  | 28 | X
2013-06-16 |  |  |  | 29 | X
2013-06-17 |  |  |  | 30 | X
2013-06-18 |  |  |  | 31 | X
2013-06-19 |  |  |  | 32 | X
2013-06-20 |  |  |  | 33 | X
2013-06-21 |  |  |  | 34 | X
2013-06-22 |  |  |  | 35 | X
2013-06-23 |  |  |  | 36 | X
2013-06-24 |  |  |  | 37 | X
2013-06-25 |  |  |  | 38 | X
2013-06-26 |  |  |  | 39 | X
2013-06-27 |  |  |  | 40 | X
2013-06-28 |  |  |  | 41 | X
2013-06-29 |  |  |  | 42 | X
2013-06-30 |  |  |  | 43 | X
2013-07-01 |  |  |  | 44 | X
2013-07-02 |  |  |  | 45 | X
2013-07-03 |  |  |  | 46 | X
2013-07-04 |  |  |  | 47 | X
2013-07-05 |  |  |  | 48 | X
2013-07-06 |  |  |  | 49 | X
2013-07-07 |  |  |  | 50 | X
2013-07-08
2013-07-09
2013-07-10
2013-07-11
2013-07-12
2013-07-13
2013-07-14
2013-07-15
2013-07-16
2013-07-17
2013-07-18
2013-07-19
2013-07-20
2013-07-21
2013-07-22
2013-07-23
2013-07-24
2013-07-25
2013-07-26
2013-07-27
2013-07-28
2013-07-29
2013-07-30
2013-07-31
2013-08-01
2013-08-02
2013-08-03
2013-08-04
2013-08-05
2013-08-06
2013-08-07
2013-08-08
2013-08-09
2013-08-10
2013-08-11
2013-08-12
2013-08-13
2013-08-14
2013-08-15
2013-08-16
2013-08-17
2013-08-18
2013-08-19
2013-08-20
2013-08-21
2013-08-22
2013-08-23
2013-08-24
2013-08-25
2013-08-26
2013-08-27
2013-08-28
2013-08-29
2013-08-30
2013-08-31
2013-09-01
2013-09-02
2013-09-03
2013-09-04
2013-09-05
2013-09-06
2013-09-07
2013-09-08
2013-09-09
2013-09-10
2013-09-11
2013-09-12
2013-09-13
2013-09-14
2013-09-15
2013-09-16
2013-09-17
2013-09-18
2013-09-19
2013-09-20
2013-09-21
2013-09-22
2013-09-23
2013-09-24
2013-09-25
2013-09-26
2013-09-27
2013-09-28
2013-09-29
2013-09-30
2013-10-01
2013-10-02
2013-10-03
2013-10-04
2013-10-05
Formulas:
Start Date = [Start Date, row above]+1